## Product backlog
Product backlog ID | Feature | Owner | Priority | Effort (in hours) | Status | Definition of done | Notes
1 | Create an account on the Admin Portal | Jake | Critical | 3 | Done | Creating an account on the Admin Portal adds the account to the database
2 | Log in to the Admin Portal | Jake | Critical | 3 | Done | User can successfully log in to the Admin Portal and view their account information
3 | Create an article on the Admin Portal | Jake | Critical | 3 | Done | Creating an article on the Admin Portal adds the article to the database
4 | View available articles on the Blog on desktop | Jake | Critical | 3 | To do | A user can view a summary of the articles on the Blog
5 | Read a single article on the Blog on desktop | Jake | Critical | 3 | To do | A user can view all information from a single selected article on the Blog
6 | Update an article on the Admin Portal | Jake | Medium | 2 | To do | A logged in user can select an article and update the articles fields, the updates are reflected by the database
7 | Chart that reflects article publish schedule on Admin Portal | Jake | Low | 3 | To do | The Admin Portal article summary view shows charts detailing articles published in timeline
8 | View available articles on the Admin Portal | Jake | High | 1 | Done | A logged in user can view a summary of the articles on the Admin Portal
9 | View a selected article on the Admin Portal | Jake | High | 1 | To do | A logged in user can view all information from a single selected article on the Admin Portal
10 | View article updates on the Admin Portal | Jake | Low | 2 | To do | Article changes can be viewed on the Admin Portal
11 | Logout of the Admin Portal | Jake | Medium | 0.5 | To do | A logged in user can log out of the system
12 | View an account's profile information on the Admin Portal | Jake | Low | 2 | To do
13 | Publish an Article | Jake | Medium | 2 | To do
14 | Secure the Admin Portal | Jake | Critical | 5 | To do

## Sprint 1 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | 17 | 14 | 7 | 5 | 5 | 1 | 0
In progress | 2 | 0 | 0 | 1 | 1 | 3 | 0
Done | 1 | 5 | 7 | 1 | 0 | 2 | 0
Ideal | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0
In progress | 0 | 0 | 0 | 1 | 1 | 3 | 0
Testing | 2 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 1 backlog
Product backlog ID | Feature | Sprint backlog ID | Task | Assigned to | Effort (in hours) | Status | [6 empty] | Notes
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Create an account on the Admin Portal | 1.1 | Add account model | Jake | 3 | Done
1 | Create an account on the Admin Portal | 1.2 | Create a function to create an account and add to database | Jake | 3 | Testing | Done
1 | Create an account on the Admin Portal | 1.3 | Add a view on the Admin Portal to allow an account to be created | Jake | 3 | Testing | Done
2 | Log in to the Admin Portal | 2.1 | Add login model which links to account | Jake | 3 | To do | Done
2 | Log in to the Admin Portal | 2.2 | Add a function to allow user to login to the Admin Panel with their email address | Jake | 3 | To do | Done
2 | Log in to the Admin Portal | 2.3 | Add a view on the Admin Portal to allow user to log in | Jake | 3 | To do | Done
3 | Create an article on the Admin Portal | 3.1 | Add an article model | Jake | 3 | To do | To do | Done
3 | Create an article on the Admin Portal | 3.2 | Create a function to create an article and update the database | Jake | 3 | To do | To do | Done
3 | Create an article on the Admin Portal | 3.3 | Add a view on the Admin Portal to create an article | Jake | 3 | To do | To do | Done
4 | View available articles on the Blog on desktop | 4.1 | Create function for API to get the list of articles from the database | Jake | 3 | To do | To do | To do | To do | To do | Done
4 | View available articles on the Blog on desktop | 4.2 | Create function for Blog to call API to get the article list | Jake | 3 | To do | To do | To do | To do | To do | In progress
4 | View available articles on the Blog on desktop | 4.3 | Create Blog view that shows the article list | Jake | 3 | To do | To do | To do | To do | To do | In progress
5 | Read a single article on the Blog on desktop | 5.1 | Create a function for API to retrieve a single article | Jake | 3 | To do | To do | To do | To do | To do | Done
5 | Read a single article on the Blog on desktop | 5.2 | Create a Blog view to display single article | Jake | 3 | To do | To do | To do | To do | To do | To do
6 | Update an article on the Admin Portal | 6.1 | Create a function in the Article controller to update the article and save to database | Jake | 2 | To do | To do | To do | Done
6 | Update an article on the Admin Portal | 6.2 | Create a view to update the article list on the Admin Portal | Jake | 2 | To do | To do | To do | In progress | In progress | In progress
8 | View available articles on the Admin Portal | 8.1 | Create a controller function to pass articles to the view | Jake | 1 | To do | To do | Done
8 | View available articles on the Admin Portal | 8.2 | Create a view to display the article list on the Admin Portal | Jake | 1 | To do | To do | Done
9 | View a selected article on the Admin Portal | 9.1 | Create a controller function to pass a single article to the view | Jake | 1 | To do | To do | Done
9 | View a selected article on the Admin Portal | 9.2 | Create a view to display all of a single articles information on the Admin Portal | Jake | 1 | To do | To do | Done

## Sprint 1 burndown
Dates | Ideal Burndown | Tasks Remaining | Completed Tasks
2023-12-02 | 20 | 20 | 1
2023-12-03 | 16.6667 | 19 | 5
2023-12-04 | 13.3333 | 14 | 7
2023-12-05 | 10 | 7 | 1
2023-12-06 | 6.6667 | 6 | 0
2023-12-07 | 3.3333 | 6 | 2
2023-12-08 | 0 | 4 | 0

## Template backlog
Product backlog ID | Feature | Sprint backlog ID | Task | Assigned to | Effort (in hours) | Status | [6 empty] | Notes
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Create an account on the Admin Portal | 1.1 | Add account model | Jake | 3 | To do
1 | Create an account on the Admin Portal | 1.2 | Create a function to create an account and add to database | Jake | 3 | To do
1 | Create an account on the Admin Portal | 1.3 | Add a view on the Admin Portal to allow an account to be created | Jake | 3 | To do

## Template burndown
Dates | Ideal Burndown | Tasks Remaining | Completed Tasks
2023-12-02 | 8 | 20 | 1
2023-12-03 | 6.6667 | 19 | 5
2023-12-04 | 5.3333 | 14 | 7
2023-12-05 | 4 | 7 | 1
2023-12-06 | 2.6667 | 6 | 0
2023-12-07 | 1.3333 | 6 | 2
2023-12-08 | 0 | 4 | 0

## Sprint 2 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
In progress | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Done | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Ideal | 1 | 0.83333 | 0.66667 | 0.5 | 0.33333 | 0.16667 | 0
In progress | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Testing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Sprint 3 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
In progress | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Done | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Ideal | 1 | 0.83333 | 0.66667 | 0.5 | 0.33333 | 0.16667 | 0
In progress | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Testing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## References - DO NOT CHANGE (hidden)
Critical | To do
High | In progress
Medium | Testing
Low | Done